## Orga
Task | What to do |  | Next meeting coming up
|  |  | Octo Refinement Prep | Topic | Notes
Retravailler les maquettes avec Shylesh et Norma | Need to find time to schedule regular meetings together. Plan a call with Shylesh for this. Do we need Benoit ? |  |  | Gear Management
|  |  |  | Comment allons nous construire la logique pour les Gears Characteristics que nous avons besoin ? | I have managed to understand the logic needed for the characteristics groups
Gestion du Backlog | Création des tickets |  |  | Quel impact sur les mockups ? | Proposition de mockups de solution faite
Testers les user stories
| Lundi matin Change the status and sprints values of all the backlog items to reflect the current status |  |  | SSF-143 | [MOB] Register new gear - Gear characteristics
| Lundi Matin Planifier une réunion avec la Team Octo pour revoir les éléments en challenge et PI 01 |  |  | SSF-147 | [BACK] Register new gear
Organiser les agendas |  |  |  | SSF-142 | [MOB] Register new gear - Form submission
Préparer les réunions
Préparation des Refinements | Team Octo
DG MARE
Organiser 3 amigos | ?
Cadrer des sujets flous | Offline Map What do we have right now ? Did they send us what we need ? How do we take the risk out of this ? Can we just show a super minimal version of the map ? Not clear to me where we stand today with FAV & ENZO. Have a small talk with them / Can this be done by message ?
Logs Call with Benoit
Rediger la Doc
Ecrire les business rules dans Confluence | Start writing the Business Rules on Confluence Start with Gear Management once we confirm what we want to do with the Team on monday morning
Ecrire la doc Archi / Tech dans Confluence | Talk with the Octo Team about this.
Cadrer comment faire des updates "App Data updates" | Sujet à travailler avec Devs + DG MARE
Share new Figma File | Update Figma links in Jira
Share the Figma with the Dev Team
Attention, did we agree on this ? ⬇️ Maybe write it down on the Business Rules When to load which data ? How not to block the user ? Login / Vessel choice screen / Home / Rest of the app We are loading all the data for you to use the application. Loading the application data. / Preparing the application.
TO DO Agenda for the Refinements - Almost done I need to create the meetings and send the invitations. Talk about the approach of One big session and two smaller ones. Although the session agenda file doesn’t have this planning, if you do, you’ll have to update the planning of the sessions.
Risks
| EU Login | Seems to be more complicated that we thought
| Offline Map | We don't know how to do this yet
| Logs | What does the client want, which format, which technology ?

## Weekly - TO DO
Weekly Prepation
Sprint update | Question Daily vendredi Demander à Benoît de relancer Laurent pour l’URL que nous avons besoin de récupérer. Relancer la demande de Enzo. Modification du Sprint We will change the sprint’s scope to build the INFRA because we can’t test properly if we don’t have the proper setting on AWS. - How to host the backend - How to host the self files to link it to the application in an official manner. - Weekly presentation of the new sprint
Gear Characteristics | Update the "proposition" mockups if the team aligns with this in the morning preparation | If the gear can be used by parts, then we should be able to create an option to store it this way and allow the user to declare that he used a part of the gear. For this to work, it would mean that we need to give each part of the gear an ID so we can identify it.
Gear Characteristics |  | Is this a real case ? How many times will this happen ? Will fishers take the time to select a part of the gear ? Do we need this data ? What's the value of this data ? Is it going to be exploited later ?
Ipad View | This was not in scope. The app will work but it might not be at it's best | What do we want to communicate with DG MARE ? Maybe we can add this as a nice to have if we have the time at the end of the last PI. Otherwise, what are they willing to give up if they truly want it ?
Extra charge PI - 01
Refinements Report | We are late on the rythm we should have.
| What can we do to make this work ? | New refinement schedule Two 1h refinement for big subjects Two 30 min refinements for smaller and faster user stories | Or no refinements. User needs + Regulation needs = Business Rules meetings with DG MARE Feature / User story creation for the Octo Team Refinements w/Octo Team to meet the need Backlog Sync w/ DG MARE over what we have refined with the Octo Team.
|  | Share in advance the requirements for the ticket to be ready for refinement | Business rules written in Confluence ahead with the need
Mockups ready by Shylesh
Sprint Review Presentation
Lola's Intervention | What is she going to do ? How are we going to proceed ? What's the goal ? Octo Team's need and alignment on what we need to work on together

## Backlog Items to talk with Team
Issue Type | Issue key | Issue id | Summary | Status | Epic Link | Story Points | Labels | Sprint |  | TO DO
SSF-182 |  | {DEV READY} [BACK] Endpoint to retrieve vessels data from FMC | Open | Data Exchange w/FMC | 3 | SSF_MOBILE_APP | PI 01 - EXTRA |  | A confirmer si c'est un doublon
SSF-160 |  | [MOB] Fishing Trips Widget | Open | Home Screen | 1 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA |  | On ne le fera pas en PI 01 / Fishing Widget PI 03
SSF-155 |  | {READY} [MOB] Vessel selection quick access | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA |  | On doit trouver un autre moyen de faire ceci, revoir les maquettes avec Shylesh
SSF-169 |  | [BACK] Languages MDR Ref Data | Open | Language Management | 5 | Backend, SSF_MOBILE_APP | PI 01 - EXTRA |  | On ne le fera pas en PI 01
SSF-168 |  | [MOB] Language Override | Open | Language Management | 5 | SSF_MOBILE_APP, mobile | PI 01 - EXTRA |  | Est-ce qu'on accepte de faire ceci en PI 01 ? Mon avis, on décale. A voir avec la Team Octo
SSF-185 |  | [MOB] Handle Multiple devices login | Open | Login | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA |  | On doit décider si on le fait ou pas
SSF-181 |  | {NEEDS DISCUSSION} [MOB] Retrieve user data from Identity Provider | Open | Login | 3 | SSF_MOBILE_APP | PI 01 - EXTRA |  | On ne le fera pas Je supprime le ticket
SSF-178 |  | [MOB] Logout | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA |  | Il faudra faire le logout mais quand ? C'est un sujet à finir de préparer/refiner EU Login / Logout ce n'est pas super clair. A vérifier avec les devs
SSF-177 |  | [MOB] Handle multi accounts login (case of ongoing tracking session) | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA |  | S'il faut le faire, à quel moment on le planifie ? Comment le dérisquer ? Atelier avec Octo Team ? Besoin de Tech DG MARE ?
SSF-139 |  | [MOB] Display other POI on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged |  | On doit simplifier Définir la liste de POI avec le client si besoin. Nice to have si jamais on a le temps ?
SSF-138 |  | [MOB] Display Hauls on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged |  | Ceci fait partie des Hauls, donc PI #02
SSF-137 |  | {READY} [BACK] Map Tiles - Server/Cache/CDN | Open | Map Integrations | 8 | SSF_MOBILE_APP, backend | PI 01 - To be challenged
SSF-136 |  | {READY} [MOB] Map Screen - Offline Mode | Open | Map Integrations | 8 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged
SSF-135 |  | {NEEDS DISCUSSION} [MOB] Map Screen - Display Open Sea Map Data | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged |  | Il faut définir quelle donnée on souhaite afficher de la part de Open Sea Map. Faire une proposition à DG MARE ?
SSF-200 |  | [MOB] Tech : Ajouter Crashlytics | Open | TECH REQUIREMENTS | 1 | SSF_MOBILE_APP, SSF_PI#01 | PI 01 - To be challenged |  | Définir avec Benoît exactement ce qu'il veut et sur quel plateforme Aujourd'hui ce n'est pas clair. Sujet identifié comme flou par la Team | Créer réunion avec Benoît