## JIRA DATA
INSTRUCTIONS: Paste your JIRA export here (replace rows 3 onward, keep headers in row 2)
Issue Type | Issue key | Issue id | Summary | Status | Epic Link | Story Points | Labels | Sprint | PI
Story | SSF-164 |  | [MOB] Routing from the menu to the selected element screen | Canceled | App Menu | 3 | Mobile, SSF_MOBILE_APP | SSF - PI 01
Story | SSF-163 |  | {READY} [MOB] Display the menu | Open | App Menu | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-182 |  | {DEV READY} [BACK] Endpoint to retrieve vessels data from FMC | Open | Data Exchange w/FMC | 3 | SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-196 |  | [MOB] Catches preference | Open | Departure Declaration | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-195 |  | [MOB] Declare Catches onboard | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-194 |  | [MOB] Submit Departure Declaration | Open | Departure Declaration | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-193 |  | [MOB] Departure Declaration Recap Screen | Open | Departure Declaration | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-192 |  | [BACK] Submit Departure Declaration | Open | Departure Declaration | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-191 |  | [MOB] Gears onboard | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-190 |  | [BACK] Data import endpoint | Open | Departure Declaration | 5 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-189 |  | [MOB] Departure Port selection | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-140 |  | [MOB] Vessel's Empty Gear Management Screen | Ready | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 01 | SSF_PI#02
Story | SSF-188 |  | [MOB] Error Management / Messages | Open | Gear Management | 2 | SSF_MOBILE_APP, SSF_PI#02, mobile | SSF - PI 02 | SSF_PI#02
Story | SSF-152 |  | [BACK] Error Management / Security | Open | Gear Management | 2 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-151 |  | [BACK] Delete Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-150 |  | [BACK] Edit Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-149 |  | [BACK] List of vessel's gear - Retrieval | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-148 |  | [BACK] List of vessel's gear - New Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-147 |  | [BACK] Register new gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-146 |  | [MOB] Delete Gear | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-145 |  | [MOB] Edit Gear | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-144 |  | [MOB] Vessel's Gear Screen - Gear List | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-143 |  | [MOB] Register new gear - Gear characteristics | Open | Gear Management | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF_PI#02
Story | SSF-142 |  | [MOB] Register new gear - Form submission | Open | Gear Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF_PI#02
Story | SSF-141 |  | [MOB] Register new gear - Init Creation Form | Open | Gear Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF_PI#02
Story | SSF-215 |  | [BACK] Pending Hauls - GET to retrieve the pending hauls | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-214 |  | [BACK] Add Catches - POST / PUT | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-213 |  | [BACK] Add Hauls - POST / PUT pour créer un haul | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 02 | SSF_PI#01
Story | SSF-212 |  | [MOB] Add hauls - Gear haul form screen | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-211 |  | [MOB] Add Catches - Form weight, number of individual, size class, discarded | Open | Hauls | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-210 |  | [MOB] Add Catches - Review screen | Open | Hauls | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-209 |  | [MOB] Add Catches - Form for discarded catches (reason, weight etc) | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-208 |  | [MOB] Add catches - Form search species and select | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-207 |  | [MOB] Add hauls - Gear set gear selection | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-206 |  | [MOB] Add hauls - Gear set map view | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-205 |  | [MOB] Hauls screen | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-160 |  | [MOB] Fishing Trips Widget | Open | Home Screen | 1 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-155 |  | {READY} [MOB] Vessel selection quick access | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-184 |  | TO UPDATE - [MOB] Session & Network Widget - Reconnection Logic | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-173 |  | [MOB] Home Screen (Mocked) | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-153 |  | TO UPDATE - [MOB] Session & Network Widget | Ready | Home Screen | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-175 |  | {DEV READY} [MOB] Setup AWS for Login redirect URI (App link, Universal Link) | Ready | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-104 |  | {DEV READY} [BACK] Gitlab CI for Ansible | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF_PI#01
Story | SSF-103 |  | {DEV READY} [BACK] Deploy App Server on AWS (Ansible) | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF_PI#01
Story | SSF-100 |  | {DEV READY} [BACK] Infra as Code implementation on AWS (Terraform) | In review | INFRA | 5 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF_PI#01
Story | SSF-99 |  | {DEV READY} [BACK] Initiate CI/CD | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-98 |  | {DEV READY} [MOB] Initiate CI/CD | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-169 |  | [BACK] Languages MDR Ref Data | Open | Language Management | 5 | Backend, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-168 |  | [MOB] Language Override | Open | Language Management | 5 | SSF_MOBILE_APP, mobile | PI 01 - EXTRA
Story | SSF-167 |  | [MOB] Initialization of internationalization | Done | Language Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-185 |  | [MOB] Handle Multiple devices login | Open | Login | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-181 |  | {NEEDS DISCUSSION} [MOB] Retrieve user data from Identity Provider | Open | Login | 3 | SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-178 |  | [MOB] Logout | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-177 |  | [MOB] Handle multi accounts login (case of ongoing tracking session) | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA
Story | SSF-203 |  | [MOB] Implement Refresh Session | Open | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-202 |  | [MOB] Vessel selection screen Errors Management | Open | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-120 |  | [BACK] Endpoint GET vessels for the user | Ready | Login | 5 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF_PI#01
Story | SSF-118 |  | [MOB] Vessel selection screen (Mocked) | Done | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-116 |  | [MOB] Implement OIDC Flow (with DPoP) | In review | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-115 |  | [MOB] Landing Page with Login button | Done | Login | 1 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-174 |  | [MOB] Get Vessels from App Server | Ready | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 02 | SSF_PI#01
Story | SSF-119 |  | [BACK] Validate requests from client | Ready | Login | 3 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 02 | SSF_PI#01
Story | SSF-117 |  | [MOB] Auto login routing | Ready | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 02 | SSF_PI#01
Story | SSF-176 |  | [MOB] Login Routing - No vessel edge case | Ready | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-187 |  | [BACK] Audit logs generation and storage | Open | Logs | 5 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-186 |  | [BACK] Backend's status Endpoint | Open | Logs | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF_PI#02
Story | SSF-139 |  | [MOB] Display other POI on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged
Story | SSF-138 |  | [MOB] Display Hauls on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged
Story | SSF-137 |  | {READY} [BACK] Map Tiles - Server/Cache/CDN | Open | Map Integrations | 8 | SSF_MOBILE_APP, backend | PI 01 - To be challenged
Story | SSF-136 |  | {READY} [MOB] Map Screen - Offline Mode | Open | Map Integrations | 8 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged
Story | SSF-135 |  | {NEEDS DISCUSSION} [MOB] Map Screen - Display Open Sea Map Data | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged
Story | SSF-134 |  | [MOB] Map Screen - Display Vessel's Current trajectory | Ready | Map Integrations | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-133 |  | [MOB] Map Widget Initialization + Current position Display | Ready | Map Integrations | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-200 |  | [MOB] Tech : Ajouter Crashlytics | Open | TECH REQUIREMENTS | 1 | SSF_MOBILE_APP, SSF_PI#01 | PI 01 - To be challenged | SSF_PI#01
Story | SSF-201 |  | [MOB] Créer un keystore pour signer l'application Android | To Deploy | TECH REQUIREMENTS | 1 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-199 |  | [MOB] Testers information / Setup | To Deploy | TECH REQUIREMENTS |  | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-112 |  | [DG MARE] Firebase Project Setup | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-111 |  | [DG MARE] AWS access | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-110 |  | [DG MARE] Gitlab Server | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-109 |  | [BACK] App Server architecture | Ready | TECH REQUIREMENTS | 4 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF_PI#01
Story | SSF-108 |  | [BACK] Initiate App Server Codebase | In Progress | TECH REQUIREMENTS | 3 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF_PI#01
Story | SSF-107 |  | [MOB] Initiate Mobile App Codebase | Done | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01, mobile | SSF - 01 | SSF_PI#01
Story | SSF-106 |  | [MOB] Initiate Firebase project with App distribution | Done | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-85 |  | [MOB] Mobile App architecture | Done | TECH REQUIREMENTS | 4 | MOBILE, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF_PI#01
Story | SSF-179 |  | {DEV READY} [BACK] Swagger setup | Open | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF_PI#01
Story | SSF-113 |  | [DG MARE] Create Apple Developper Account | Open | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP | SSF - PI 01
Story | SSF-158 |  | [MOB] Location services authorization request | Ready | Vessel Tracking | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-90 |  | [MOB] Send tracking records | Ready | Vessel Tracking | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-89 |  | [BACK] Receive Vessel tracking Data | Ready | Vessel Tracking | 3 | Backend, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-88 |  | [MOB] Tracking Records | Ready | Vessel Tracking | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01
Story | SSF-87 |  | [MOB] Geolocation Widget | Ready | Vessel Tracking | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF_PI#01

## DASHBOARD
REFINEMENT TRACKER - DASHBOARD
Last Updated |  | Current Sprint | 1
QUICK METRICS
Total Stories Whole Backlog |  |  |  | Status
To Refine (Open) |  |  |  | Risk Level
Already Refined (Ready)
Completed So Far |  |  |  | Current Velocity
Remaining |  |  |  | Target Velocity | 6.5
Progress % |  |  |  | Projected Completion
SESSION SUMMARY (LAST 3)
| Session | Sprint | Date | Stories Refined | Cumulative | Status
WEEKLY REPORT (Auto-Generated)
Report Text
📊 PI PROGRESS
See PI PROGRESS sheet for detailed PI tracking →
📊 PI PROGRESS
See PI PROGRESS sheet for PI tracking →

## PI PROGRESS
PI PROGRESS TRACKER
PI Label | Total Stories | Refined (Ready) | To Refine (Open) | Other Status | % Complete | Progress | Status
SSF_PI#01
SSF_PI#02

## SESSION CALENDAR
SESSION CALENDAR - All 13 Remaining Sessions
Session # | Sprint | Week | Date | Time | Duration | Target | Prep Deadline | Status | Notes
3 | 1 | 2 | 2025-11-12 | 10:00 | 60 | 7 |  | 🟡 This Week
4 | 2 | 1 | 2025-11-19 |  | 60 | 7 |  | 🟢 Upcoming
5 | 2 | 1 | 2025-11-21 |  | 60 | 7 |  | 🟢 Upcoming
6 | 2 | 2 | 2025-11-26 |  | 60 | 7 |  | 🟢 Upcoming
7 | 3 | 1 | 2025-12-03 |  | 60 | 7 |  | 🟢 Upcoming
8 | 3 | 1 | 2025-12-05 |  | 60 | 7 |  | 🟢 Upcoming
9 | 3 | 2 | 2025-12-10 |  | 60 | 7 |  | 🟢 Upcoming
10 | 4 | 1 | 2025-12-17 |  | 60 | 7 |  | 🟢 Upcoming
11 | 4 | 1 | 2025-12-19 |  | 60 | 7 |  | 🟢 Upcoming
12 | 4 | 2 | 2025-12-24 |  | 60 | 7 |  | 🟢 Upcoming
13 | 5 | 1 | 2026-01-07 |  | 60 | 7 |  | 🟢 Upcoming
14 | 5 | 1 | 2026-01-09 |  | 60 | 7 |  | 🟢 Upcoming
15 | 5 | 2 | 2026-01-14 |  | 60 | 7 |  | 🟢 Upcoming

## SESSIONS AGENDA
Refinement session #03 - 12/11/2025
Date | 2025-11-12
Time | 10:00
Topics | Gear Management
Goal | All items must be "Ready" by the end of Sprint #02
Sprint | 2
Agenda for Refinement session #03
Story Number | Summary | Status
SSF-141 | [MOB] Register new gear - Init Creation Form | Ready
SSF-144 | [MOB] Vessel's Gear Screen - Gear List | Ready
Gear Characteristics Workshop - 13/11/2025
Date
Sprint | 2
Agenda for the Workshop
Refinement session #04
Date | 2025-11-12
Time | 10:00
Topics | Gear Management
Goal | All items must be "Ready" by the end of Sprint #02
Sprint | 2
Agenda for Refinement session #04
Story Number | Summary | Status
SSF-143 | [MOB] Register new gear - Gear characteristics | Open
SSF-147 | [BACK] Register new gear | Open
SSF-142 | [MOB] Register new gear - Form submission | Open
SSF-148 | [BACK] List of vessel's gear - New Gear | Open
SSF-149 | [BACK] List of vessel's gear - Retrieval | Open
SSF-145 | [MOB] Edit Gear | Open
SSF-150 | [BACK] Edit Gear | Open
SSF-188 | [MOB] Error Management / Messages | Open
SSF-152 | [BACK] Error Management / Security | Open
SSF-146 | [MOB] Delete Gear | Open
SSF-151 | [BACK] Delete Gear | Open
Refinement session #05
Date
Time
Topics | Departure Declaration
Goal | All items must be "Ready" by the end of Sprint #03
Sprint | 3
Agenda for Refinement session #05
Story Number | Summary | Status
? | We don't have a Home screen button for the Departure Declaration | ? | Departure Declaration
SSF-189 | [MOB] Departure Port selection | Open | Departure Declaration
SSF-191 | [MOB] Gears onboard | Open | Departure Declaration
SSF-195 | [MOB] Declare Catches onboard | Open | Departure Declaration
SSF-196 | [MOB] Catches preference | Open | Departure Declaration
Refinement session #06
Date
Time
Topics | Departure Declaration |  |  | Hauls
Goal | All the user stories in the agenda are "Ready"
Sprint | 3
Agenda for Refinement session #06
Story Number | Summary | Status
SSF-190 | [BACK] Data import endpoint | Open | Departure Declaration
SSF-193 | [MOB] Departure Declaration Recap Screen | Open | Departure Declaration
SSF-194 | [MOB] Submit Departure Declaration | Open | Departure Declaration
SSF-192 | [BACK] Submit Departure Declaration | Open | Departure Declaration
Refinement session #07
Date
Time
Topics | Hauls
Goal | All the user stories in the agenda are "Ready"
Sprint | 3
Agenda for Refinement session #07
Story Number | Summary | Status
SSF-205 | [MOB] Hauls screen | Open | Hauls
SSF-207 | [MOB] Add hauls - Gear set gear selection | Open | Hauls
SSF-206 | [MOB] Add hauls - Gear set map view | Open | Hauls
SSF-213 | [BACK] Add Hauls - POST / PUT pour créer un haul | Open | Hauls
SSF-212 | [MOB] Add hauls - Gear haul form screen | Open | Hauls
Refinement session #08
Date
Time
Topics | Hauls
Goal | All the user stories in the agenda are "Ready"
Sprint | 4
Agenda for Refinement session #08
Story Number | Summary | Status
SSF-211 | [MOB] Add Catches - Form weight, number of individual, size class, discarded | Open | Hauls
SSF-209 | [MOB] Add Catches - Form for discarded catches (reason, weight etc) | Open | Hauls
SSF-208 | [MOB] Add catches - Form search species and select | Open | Hauls
SSF-214 | [BACK] Add Catches - POST / PUT | Open | Hauls
SSF-210 | [MOB] Add Catches - Review screen | Open | Hauls
Refinement session #09
Date
Time
Topics | Hauls
Goal | All the user stories in the agenda are "Ready"
Sprint | 4
Agenda for Refinement session #09
Story Number | Summary | Status
SSF-215 | [BACK] Pending Hauls - GET to retrieve the pending hauls | Open

## SESSION LOG
SESSION LOG - Data Entry (Update After Each Session)
Session # | Sprint | Date | Target Stories | Stories Refined (ENTER THIS) | Cumulative | Remaining | Velocity | Status | PI(s) Worked
1 | 1 | 2025-11-05 | 7 | 0 |  |  |  |  | Enter PI labels: SSF_PI#01, SSF_PI#02, etc.
2 | 1 | 2025-11-07 | 7 | 1 |  |  |  |  | Team alignment
3 | 1 | 2025-11-12 | 7 | 2 |  |  |  |  | Gear Management
4 | 2 | 2025-11-19 | 7
5 | 2 | 2025-11-21 | 7
6 | 2 | 2025-11-26 | 7
7 | 3 | 2025-12-03 | 7
8 | 3 | 2025-12-05 | 7
9 | 3 | 2025-12-10 | 7
10 | 4 | 2025-12-17 | 7
11 | 4 | 2025-12-19 | 7
12 | 4 | 2025-12-24 | 7
13 | 5 | 2026-01-07 | 7
14 | 5 | 2026-01-09 | 7
15 | 5 | 2026-01-14 | 7
INSTRUCTIONS: Update ONLY column F after each session. Everything else auto-calculates!

## BURNDOWN CHART DATA
TARGET SESSIONS:
BURNDOWN CHART DATA
Session # | Sprint | IDEAL Stories Remaining | ACTUAL Stories Remaining | Variance | Status
0 | 1 |  |  | 0 | Start

## EPIC PROGRESS
EPIC PROGRESS - Auto-calculated from JIRA DATA
Epic ID | Epic Name | Total | Open | Ready | Other | % Complete | Priority | Sprint | PI Filter | Refined in PI | Total in PI | PI Progress
App Menu | App Menu
Data Exchange w/FMC | Data Exchange w/FMC
Departure Declaration | Departure Declaration
Gear Management | Gear Management
Hauls | Hauls
Home Screen | Home Screen
INFRA | INFRA
Language Management | Language Management
Login | Login
Logs | Logs
Map Integrations | Map Integrations
TECH REQUIREMENTS | TECH REQUIREMENTS
Vessel Tracking | Vessel Tracking

## BURNUP CHART DATA
BURNUP CHART DATA
Session # | Sprint | Stories Refined (Target) | Stories Refined (Actual) | Total Scope | Gap
0 | 1 | 0 | 0 |  | 0

## SSF_PI#01 SESSION LOG
SSF_PI#01 REFINEMENT SESSION LOG
Session # | Sprint | Date | PI(s) Worked | Target Stories | Stories Refined | Cumulative | Remaining | Velocity
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17

## SSF_PI#01 BURNDOWN
TARGET SESSIONS: | 15 |  | SSF_PI#01 BURNDOWN DATA
TOTAL STORIES:
Session # | Sprint | IDEAL Remaining | ACTUAL Remaining | Variance | TO CREATE CHART:
0 |  |  |  |  | 1. Select cells C4:D21
1 |  |  |  |  | 2. Insert > Chart > Line
2 |  |  |  |  | 3. Title: See cell D1
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## SSF_PI#02 SESSION LOG
SSF_PI#02 REFINEMENT SESSION LOG
Session # | Sprint | Date | PI(s) Worked | Target Stories | Stories Refined | Cumulative | Remaining | Velocity
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17

## SSF_PI#02 BURNDOWN
TARGET SESSIONS: | 15 |  | SSF_PI#02 BURNDOWN DATA
TOTAL STORIES:
Session # | Sprint | IDEAL Remaining | ACTUAL Remaining | Variance | TO CREATE CHART:
0 |  |  |  |  | 1. Select cells C4:D21
1 |  |  |  |  | 2. Insert > Chart > Line
2 |  |  |  |  | 3. Title: See cell D1
3
4
5
6
7
8
9
10
11
12
13
14
15
16