## SSF_BACKLOG_EXPORT_10_11.xls
[8 empty] | issueKey | issueKey | summary | jiraUrl | Filtered issueKey | Filtered Summary | Filtered JiraUrl
CITnet Jira | [7 empty] | SSF-84 | SSF-99 | Tech Requirements | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-84
Displaying 91 issues at 10/Nov/25 17:59. | [7 empty] | SSF-97 | SSF-98 | Infra | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-97
Issue Type | issueKey | Summary | Status | Epic Link | Story Points | Labels | Sprint | SSF-96 | SSF-90 | Login | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-96
Story | SSF-164 | [MOB] Routing from the menu to the selected element screen | Canceled | App Menu | 3 | Mobile, SSF_MOBILE_APP | SSF - PI 01 | SSF-94 | SSF-89 | Home Screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-94
Story | SSF-163 | {READY} [MOB] Display the menu | Open | App Menu | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-95 | SSF-88 | Map Integrations | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-95
Story | SSF-182 | {DEV READY} [BACK] Endpoint to retrieve vessels data from FMC | Open | Data Exchange w/FMC | 3 | SSF_MOBILE_APP | PI 01 - EXTRA | SSF-86 | SSF-87 | Vessel Tracking | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-86
Story | SSF-196 | [MOB] Catches preference | Open | Departure Declaration | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-110 | SSF-85 | [DG MARE] Gitlab Server | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-110 | SSF-110 | [DG MARE] Gitlab Server | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-110
Story | SSF-195 | [MOB] Declare Catches onboard | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-111 | SSF-215 | [DG MARE] AWS access | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-111 | SSF-111 | [DG MARE] AWS access | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-111
Story | SSF-194 | [MOB] Submit Departure Declaration | Open | Departure Declaration | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-112 | SSF-214 | [DG MARE] Firebase Project Setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-112 | SSF-112 | [DG MARE] Firebase Project Setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-112
Story | SSF-193 | [MOB] Departure Declaration Recap Screen | Open | Departure Declaration | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-107 | SSF-213 | [MOB] Initiate Mobile App Codebase | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-107 | SSF-107 | [MOB] Initiate Mobile App Codebase | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-107
Story | SSF-192 | [BACK] Submit Departure Declaration | Open | Departure Declaration | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-85 | SSF-212 | [MOB] Mobile App architecture | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-85 | SSF-85 | [MOB] Mobile App architecture | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-85
Story | SSF-191 | [MOB] Gears onboard | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-106 | SSF-211 | [MOB] Initiate Firebase project with App distribution | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-106 | SSF-106 | [MOB] Initiate Firebase project with App distribution | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-106
Story | SSF-190 | [BACK] Data import endpoint | Open | Departure Declaration | 5 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-116 | SSF-210 | [MOB] Implement OIDC Flow (with DPoP) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-116 | SSF-116 | [MOB] Implement OIDC Flow (with DPoP) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-116
Story | SSF-189 | [MOB] Departure Port selection | Open | Departure Declaration | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-115 | SSF-209 | [MOB] Landing Page with Login button | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-115 | SSF-115 | [MOB] Landing Page with Login button | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-115
Story | SSF-140 | [MOB] Vessel's Empty Gear Management Screen | Ready | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 01 | SSF-118 | SSF-208 | [MOB] Vessel selection screen (Mocked) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-118 | SSF-118 | [MOB] Vessel selection screen (Mocked) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-118
Story | SSF-188 | [MOB] Error Management / Messages | Open | Gear Management | 2 | SSF_MOBILE_APP, SSF_PI#02, mobile | SSF - PI 02 | SSF-167 | SSF-207 | [MOB] Initialization of internationalization | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-167 | SSF-167 | [MOB] Initialization of internationalization | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-167
Story | SSF-152 | [BACK] Error Management / Security | Open | Gear Management | 2 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-201 | SSF-206 | [MOB] Créer un keystore pour signer l'application Android | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-201 | SSF-201 | [MOB] Créer un keystore pour signer l'application Android | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-201
Story | SSF-151 | [BACK] Delete Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-199 | SSF-205 | [MOB] Testers information / Setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-199 | SSF-199 | [MOB] Testers information / Setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-199
Story | SSF-150 | [BACK] Edit Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-113 | SSF-203 | [DG MARE] Create Apple Developper Account | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-113 | SSF-113 | [DG MARE] Create Apple Developper Account | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-113
Story | SSF-149 | [BACK] List of vessel's gear - Retrieval | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-175 | SSF-202 | {DEV READY} [MOB] Setup AWS for Login redirect URI (App link, Universal Link) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-175 | SSF-175 | {DEV READY} [MOB] Setup AWS for Login redirect URI (App link, Universal Link) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-175
Story | SSF-148 | [BACK] List of vessel's gear - New Gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-203 | SSF-201 | [MOB] Implement Refresh Session | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-203 | SSF-203 | [MOB] Implement Refresh Session | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-203
Story | SSF-147 | [BACK] Register new gear | Open | Gear Management | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-179 | SSF-200 | {DEV READY} [BACK] Swagger setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-179 | SSF-179 | {DEV READY} [BACK] Swagger setup | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-179
Story | SSF-146 | [MOB] Delete Gear | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-98 | SSF-199 | {DEV READY} [MOB] Initiate CI/CD | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-98 | SSF-98 | {DEV READY} [MOB] Initiate CI/CD | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-98
Story | SSF-145 | [MOB] Edit Gear | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-99 | SSF-196 | {DEV READY} [BACK] Initiate CI/CD | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-99 | SSF-99 | {DEV READY} [BACK] Initiate CI/CD | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-99
Story | SSF-144 | [MOB] Vessel's Gear Screen - Gear List | Open | Gear Management | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-100 | SSF-195 | {DEV READY} [BACK] Infra as Code implementation on AWS (Terraform) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-100 | SSF-100 | {DEV READY} [BACK] Infra as Code implementation on AWS (Terraform) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-100
Story | SSF-143 | [MOB] Register new gear - Gear characteristics | Open | Gear Management | 5 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF-103 | SSF-194 | {DEV READY} [BACK] Deploy App Server on AWS (Ansible) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-103 | SSF-103 | {DEV READY} [BACK] Deploy App Server on AWS (Ansible) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-103
Story | SSF-142 | [MOB] Register new gear - Form submission | Open | Gear Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF-104 | SSF-193 | {DEV READY} [BACK] Gitlab CI for Ansible | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-104 | SSF-104 | {DEV READY} [BACK] Gitlab CI for Ansible | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-104
Story | SSF-141 | [MOB] Register new gear - Init Creation Form | Open | Gear Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - TO REFINE | SSF-173 | SSF-192 | [MOB] Home Screen (Mocked) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-173 | SSF-173 | [MOB] Home Screen (Mocked) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-173
Story | SSF-215 | [BACK] Pending Hauls - GET to retrieve the pending hauls | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-93 | SSF-191 | Gear Management | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-93
Story | SSF-214 | [BACK] Add Catches - POST / PUT | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-124 | SSF-190 | Fishing Trips 01 - Creation and start | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-124
Story | SSF-213 | [BACK] Add Hauls - POST / PUT pour créer un haul | Open | Hauls | 3 | Backend, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 02 | SSF-122 | SSF-189 | Departure Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-122
Story | SSF-212 | [MOB] Add hauls - Gear haul form screen | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-123 | SSF-188 | Hauls | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-123
Story | SSF-211 | [MOB] Add Catches - Form weight, number of individual, size class, discarded | Open | Hauls | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-121 | SSF-187 | Lost Fishing Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-121
Story | SSF-210 | [MOB] Add Catches - Review screen | Open | Hauls | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-125 | SSF-186 | Logbook | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-125
Story | SSF-209 | [MOB] Add Catches - Form for discarded catches (reason, weight etc) | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-126 | SSF-185 | Return to Port Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-126
Story | SSF-208 | [MOB] Add catches - Form search species and select | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-159 | SSF-184 | Fishing Trips 02 - Ending and history management | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-159
Story | SSF-207 | [MOB] Add hauls - Gear set gear selection | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-127 | SSF-182 | Landing Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-127
Story | SSF-206 | [MOB] Add hauls - Gear set map view | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-128 | SSF-181 | Third Party Waters / Effort Zones | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-128
Story | SSF-205 | [MOB] Hauls screen | Open | Hauls | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-129 | SSF-179 | Transhipment | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-129
Story | SSF-160 | [MOB] Fishing Trips Widget | Open | Home Screen | 1 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-130 | SSF-178 | Admin Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-130
Story | SSF-155 | {READY} [MOB] Vessel selection quick access | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-131 | SSF-177 | App Parameters | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-131
Story | SSF-184 | TO UPDATE - [MOB] Session & Network Widget - Reconnection Logic | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-132 | SSF-176 | Data Exchange w/FMC | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-132
Story | SSF-173 | [MOB] Home Screen (Mocked) | Ready | Home Screen | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-134 | SSF-175 | [MOB] Map Screen - Display Vessel's Current trajectory | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-134 | SSF-134 | [MOB] Map Screen - Display Vessel's Current trajectory | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-134
Story | SSF-153 | TO UPDATE - [MOB] Session & Network Widget | Ready | Home Screen | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-155 | SSF-174 | {READY} [MOB] Vessel selection quick access | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-155 | SSF-155 | {READY} [MOB] Vessel selection quick access | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-155
Story | SSF-175 | {DEV READY} [MOB] Setup AWS for Login redirect URI (App link, Universal Link) | Ready | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-178 | SSF-173 | [MOB] Logout | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-178 | SSF-178 | [MOB] Logout | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-178
Story | SSF-104 | {DEV READY} [BACK] Gitlab CI for Ansible | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF-177 | SSF-169 | [MOB] Handle multi accounts login (case of ongoing tracking session) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-177 | SSF-177 | [MOB] Handle multi accounts login (case of ongoing tracking session) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-177
Story | SSF-103 | {DEV READY} [BACK] Deploy App Server on AWS (Ansible) | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF-168 | SSF-168 | [MOB] Language Override | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-168 | SSF-168 | [MOB] Language Override | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-168
Story | SSF-100 | {DEV READY} [BACK] Infra as Code implementation on AWS (Terraform) | In review | INFRA | 5 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF-160 | SSF-167 | [MOB] Fishing Trips Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-160 | SSF-160 | [MOB] Fishing Trips Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-160
Story | SSF-99 | {DEV READY} [BACK] Initiate CI/CD | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-182 | SSF-164 | {DEV READY} [BACK] Endpoint to retrieve vessels data from FMC | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-182 | SSF-182 | {DEV READY} [BACK] Endpoint to retrieve vessels data from FMC | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-182
Story | SSF-98 | {DEV READY} [MOB] Initiate CI/CD | Open | INFRA | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-140 | SSF-163 | [MOB] Vessel's Empty Gear Management Screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-140 | SSF-140 | [MOB] Vessel's Empty Gear Management Screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-140
Story | SSF-169 | [BACK] Languages MDR Ref Data | Open | Language Management | 5 | Backend, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-141 | SSF-160 | [MOB] Register new gear - Init Creation Form | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-141 | SSF-141 | [MOB] Register new gear - Init Creation Form | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-141
Story | SSF-168 | [MOB] Language Override | Open | Language Management | 5 | SSF_MOBILE_APP, mobile | PI 01 - EXTRA | SSF-142 | SSF-158 | [MOB] Register new gear - Form submission | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-142 | SSF-142 | [MOB] Register new gear - Form submission | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-142
Story | SSF-167 | [MOB] Initialization of internationalization | Done | Language Management | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-143 | SSF-155 | [MOB] Register new gear - Gear characteristics | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-143 | SSF-143 | [MOB] Register new gear - Gear characteristics | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-143
Story | SSF-185 | [MOB] Handle Multiple devices login | Open | Login | 2 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-144 | SSF-153 | [MOB] Vessel's Gear Screen - Gear List | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-144 | SSF-144 | [MOB] Vessel's Gear Screen - Gear List | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-144
Story | SSF-181 | {NEEDS DISCUSSION} [MOB] Retrieve user data from Identity Provider | Open | Login | 3 | SSF_MOBILE_APP | PI 01 - EXTRA | SSF-145 | SSF-152 | [MOB] Edit Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-145 | SSF-145 | [MOB] Edit Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-145
Story | SSF-178 | [MOB] Logout | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-146 | SSF-151 | [MOB] Delete Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-146 | SSF-146 | [MOB] Delete Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-146
Story | SSF-177 | [MOB] Handle multi accounts login (case of ongoing tracking session) | Open | Login | 5 | Mobile, SSF_MOBILE_APP | PI 01 - EXTRA | SSF-147 | SSF-150 | [BACK] Register new gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-147 | SSF-147 | [BACK] Register new gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-147
Story | SSF-203 | [MOB] Implement Refresh Session | Open | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-148 | SSF-149 | [BACK] List of vessel's gear - New Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-148 | SSF-148 | [BACK] List of vessel's gear - New Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-148
Story | SSF-202 | [MOB] Vessel selection screen Errors Management | Open | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-150 | SSF-148 | [BACK] Edit Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-150 | SSF-150 | [BACK] Edit Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-150
Story | SSF-120 | [BACK] Endpoint GET vessels for the user | Ready | Login | 5 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF-149 | SSF-147 | [BACK] List of vessel's gear - Retrieval | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-149 | SSF-149 | [BACK] List of vessel's gear - Retrieval | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-149
Story | SSF-118 | [MOB] Vessel selection screen (Mocked) | Done | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-151 | SSF-146 | [BACK] Delete Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-151 | SSF-151 | [BACK] Delete Gear | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-151
Story | SSF-116 | [MOB] Implement OIDC Flow (with DPoP) | In review | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-152 | SSF-145 | [BACK] Error Management / Security | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-152 | SSF-152 | [BACK] Error Management / Security | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-152
Story | SSF-115 | [MOB] Landing Page with Login button | Done | Login | 1 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-188 | SSF-144 | [MOB] Error Management / Messages | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-188 | SSF-188 | [MOB] Error Management / Messages | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-188
Story | SSF-174 | [MOB] Get Vessels from App Server | Ready | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 02 | SSF-186 | SSF-143 | [BACK] Backend's status Endpoint | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-186 | SSF-186 | [BACK] Backend's status Endpoint | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-186
Story | SSF-119 | [BACK] Validate requests from client | Ready | Login | 3 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 02 | SSF-187 | SSF-142 | [BACK] Audit logs generation and storage | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-187 | SSF-187 | [BACK] Audit logs generation and storage | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-187
Story | SSF-117 | [MOB] Auto login routing | Ready | Login | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - 02 | SSF-163 | SSF-141 | {READY} [MOB] Display the menu | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-163 | SSF-163 | {READY} [MOB] Display the menu | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-163
Story | SSF-176 | [MOB] Login Routing - No vessel edge case | Ready | Login | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-189 | SSF-140 | [MOB] Departure Port selection | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-189 | SSF-189 | [MOB] Departure Port selection | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-189
Story | SSF-187 | [BACK] Audit logs generation and storage | Open | Logs | 5 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-190 | SSF-139 | [BACK] Data import endpoint | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-190 | SSF-190 | [BACK] Data import endpoint | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-190
Story | SSF-186 | [BACK] Backend's status Endpoint | Open | Logs | 3 | Backend, SSF_MOBILE_APP, SSF_PI#02 | SSF - PI 02 | SSF-191 | SSF-138 | [MOB] Gears onboard | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-191 | SSF-191 | [MOB] Gears onboard | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-191
Story | SSF-139 | [MOB] Display other POI on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged | SSF-192 | SSF-137 | [BACK] Submit Departure Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-192 | SSF-192 | [BACK] Submit Departure Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-192
Story | SSF-138 | [MOB] Display Hauls on the map | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged | SSF-193 | SSF-136 | [MOB] Departure Declaration Recap Screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-193 | SSF-193 | [MOB] Departure Declaration Recap Screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-193
Story | SSF-137 | {READY} [BACK] Map Tiles - Server/Cache/CDN | Open | Map Integrations | 8 | SSF_MOBILE_APP, backend | PI 01 - To be challenged | SSF-194 | SSF-135 | [MOB] Submit Departure Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-194 | SSF-194 | [MOB] Submit Departure Declaration | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-194
Story | SSF-136 | {READY} [MOB] Map Screen - Offline Mode | Open | Map Integrations | 8 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged | SSF-195 | SSF-134 | [MOB] Declare Catches onboard | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-195 | SSF-195 | [MOB] Declare Catches onboard | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-195
Story | SSF-135 | {NEEDS DISCUSSION} [MOB] Map Screen - Display Open Sea Map Data | Open | Map Integrations | 3 | Mobile, SSF_MOBILE_APP | PI 01 - To be challenged | SSF-196 | SSF-133 | [MOB] Catches preference | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-196 | SSF-196 | [MOB] Catches preference | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-196
Story | SSF-134 | [MOB] Map Screen - Display Vessel's Current trajectory | Ready | Map Integrations | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-205 | SSF-120 | [MOB] Hauls screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-205 | SSF-205 | [MOB] Hauls screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-205
Story | SSF-133 | [MOB] Map Widget Initialization + Current position Display | Ready | Map Integrations | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-206 | SSF-119 | [MOB] Add hauls - Gear set map view | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-206 | SSF-206 | [MOB] Add hauls - Gear set map view | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-206
Story | SSF-200 | [MOB] Tech : Ajouter Crashlytics | Open | TECH REQUIREMENTS | 1 | SSF_MOBILE_APP, SSF_PI#01 | PI 01 - To be challenged | SSF-207 | SSF-118 | [MOB] Add hauls - Gear set gear selection | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-207 | SSF-207 | [MOB] Add hauls - Gear set gear selection | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-207
Story | SSF-201 | [MOB] Créer un keystore pour signer l'application Android | To Deploy | TECH REQUIREMENTS | 1 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-208 | SSF-117 | [MOB] Add catches - Form search species and select | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-208 | SSF-208 | [MOB] Add catches - Form search species and select | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-208
Story | SSF-199 | [MOB] Testers information / Setup | To Deploy | TECH REQUIREMENTS |  | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-209 | SSF-116 | [MOB] Add Catches - Form for discarded catches (reason, weight etc) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-209 | SSF-209 | [MOB] Add Catches - Form for discarded catches (reason, weight etc) | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-209
Story | SSF-112 | [DG MARE] Firebase Project Setup | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-210 | SSF-115 | [MOB] Add Catches - Review screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-210 | SSF-210 | [MOB] Add Catches - Review screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-210
Story | SSF-111 | [DG MARE] AWS access | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-211 | SSF-113 | [MOB] Add Catches - Form weight, number of individual, size class, discarded | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-211 | SSF-211 | [MOB] Add Catches - Form weight, number of individual, size class, discarded | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-211
Story | SSF-110 | [DG MARE] Gitlab Server | Done | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-212 | SSF-112 | [MOB] Add hauls - Gear haul form screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-212 | SSF-212 | [MOB] Add hauls - Gear haul form screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-212
Story | SSF-109 | [BACK] App Server architecture | Ready | TECH REQUIREMENTS | 4 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF-213 | SSF-111 | [BACK] Add Hauls - POST / PUT pour créer un haul | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-213 | SSF-213 | [BACK] Add Hauls - POST / PUT pour créer un haul | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-213
Story | SSF-108 | [BACK] Initiate App Server Codebase | In Progress | TECH REQUIREMENTS | 3 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - 01 | SSF-214 | SSF-110 | [BACK] Add Catches - POST / PUT | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-214 | SSF-214 | [BACK] Add Catches - POST / PUT | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-214
Story | SSF-107 | [MOB] Initiate Mobile App Codebase | Done | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01, mobile | SSF - 01 | SSF-215 | SSF-109 | [BACK] Pending Hauls - GET to retrieve the pending hauls | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-215 | SSF-215 | [BACK] Pending Hauls - GET to retrieve the pending hauls | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-215
Story | SSF-106 | [MOB] Initiate Firebase project with App distribution | Done | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-162 | SSF-108 | App Menu | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-162
Story | SSF-85 | [MOB] Mobile App architecture | Done | TECH REQUIREMENTS | 4 | MOBILE, SSF_MOBILE_APP, SSF_PI#01 | SSF - 01 | SSF-164 | SSF-107 | [MOB] Routing from the menu to the selected element screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-164 | SSF-164 | [MOB] Routing from the menu to the selected element screen | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-164
Story | SSF-179 | {DEV READY} [BACK] Swagger setup | Open | TECH REQUIREMENTS | 2 | SSF_MOBILE_APP, SSF_PI#01, backend | SSF - PI 01 | SSF-165 | SSF-106 | Logs | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-165
Story | SSF-113 | [DG MARE] Create Apple Developper Account | Open | TECH REQUIREMENTS | 1 | DG_MARE_ACTION, SSF_MOBILE_APP | SSF - PI 01 | SSF-166 | SSF-104 | Language Management | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-166
Story | SSF-158 | [MOB] Location services authorization request | Ready | Vessel Tracking | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-170 | SSF-103 | User Profile | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-170
Story | SSF-90 | [MOB] Send tracking records | Ready | Vessel Tracking | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-171 | SSF-100 | Vessel Profile | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-171
Story | SSF-89 | [BACK] Receive Vessel tracking Data | Ready | Vessel Tracking | 3 | Backend, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-176 |  | [MOB] Login Routing - No vessel edge case | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-176 | SSF-176 | [MOB] Login Routing - No vessel edge case | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-176
Story | SSF-88 | [MOB] Tracking Records | Ready | Vessel Tracking | 3 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-87 |  | [MOB] Geolocation Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-87 | SSF-87 | [MOB] Geolocation Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-87
Story | SSF-87 | [MOB] Geolocation Widget | Ready | Vessel Tracking | 2 | Mobile, SSF_MOBILE_APP, SSF_PI#01 | SSF - PI 01 | SSF-88 |  | [MOB] Tracking Records | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-88 | SSF-88 | [MOB] Tracking Records | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-88
Generated at Mon Nov 10 17:59:09 CET 2025 by PALAZZO Nicolas using Jira 9.12.10#9120010-sha1:3b20ee34958dbedd3d6f3418ef74b9ccb7acf6ef. | [7 empty] | SSF-89 |  | [BACK] Receive Vessel tracking Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-89 | SSF-89 | [BACK] Receive Vessel tracking Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-89
[8 empty] | SSF-90 |  | [MOB] Send tracking records | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-90 | SSF-90 | [MOB] Send tracking records | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-90
[8 empty] | SSF-158 |  | [MOB] Location services authorization request | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-158 | SSF-158 | [MOB] Location services authorization request | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-158
[8 empty] | SSF-133 |  | [MOB] Map Widget Initialization + Current position Display | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-133 | SSF-133 | [MOB] Map Widget Initialization + Current position Display | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-133
[8 empty] | SSF-153 |  | TO UPDATE - [MOB] Session & Network Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-153 | SSF-153 | TO UPDATE - [MOB] Session & Network Widget | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-153
[8 empty] | SSF-184 |  | TO UPDATE - [MOB] Session & Network Widget - Reconnection Logic | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-184 | SSF-184 | TO UPDATE - [MOB] Session & Network Widget - Reconnection Logic | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-184
[8 empty] | SSF-117 |  | [MOB] Auto login routing | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-117 | SSF-117 | [MOB] Auto login routing | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-117
[8 empty] | SSF-174 |  | [MOB] Get Vessels from App Server | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-174 | SSF-174 | [MOB] Get Vessels from App Server | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-174
[8 empty] | SSF-119 |  | [BACK] Validate requests from client | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-119 | SSF-119 | [BACK] Validate requests from client | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-119
[8 empty] | SSF-181 |  | {NEEDS DISCUSSION} [MOB] Retrieve user data from Identity Provider | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-181 | SSF-181 | {NEEDS DISCUSSION} [MOB] Retrieve user data from Identity Provider | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-181
[8 empty] | SSF-185 |  | [MOB] Handle Multiple devices login | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-185 | SSF-185 | [MOB] Handle Multiple devices login | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-185
[8 empty] | SSF-169 |  | [BACK] Languages MDR Ref Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-169 | SSF-169 | [BACK] Languages MDR Ref Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-169
[8 empty] | SSF-137 |  | {READY} [BACK] Map Tiles - Server/Cache/CDN | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-137 | SSF-137 | {READY} [BACK] Map Tiles - Server/Cache/CDN | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-137
[8 empty] | SSF-135 |  | {NEEDS DISCUSSION} [MOB] Map Screen - Display Open Sea Map Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-135 | SSF-135 | {NEEDS DISCUSSION} [MOB] Map Screen - Display Open Sea Map Data | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-135
[8 empty] | SSF-138 |  | [MOB] Display Hauls on the map | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-138 | SSF-138 | [MOB] Display Hauls on the map | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-138
[8 empty] | SSF-139 |  | [MOB] Display other POI on the map | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-139 | SSF-139 | [MOB] Display other POI on the map | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-139
[8 empty] | SSF-136 |  | {READY} [MOB] Map Screen - Offline Mode | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-136 | SSF-136 | {READY} [MOB] Map Screen - Offline Mode | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-136
[8 empty] | SSF-200 |  | [MOB] Tech : Ajouter Crashlytics | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-200 | SSF-200 | [MOB] Tech : Ajouter Crashlytics | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-200
[8 empty] | SSF-202 |  | [MOB] Vessel selection screen Errors Management | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-202 | SSF-202 | [MOB] Vessel selection screen Errors Management | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-202
[8 empty] | SSF-108 |  | [BACK] Initiate App Server Codebase | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-108 | SSF-108 | [BACK] Initiate App Server Codebase | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-108
[8 empty] | SSF-109 |  | [BACK] App Server architecture | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-109 | SSF-109 | [BACK] App Server architecture | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-109
[8 empty] | SSF-120 |  | [BACK] Endpoint GET vessels for the user | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-120 | SSF-120 | [BACK] Endpoint GET vessels for the user | https://citnet.tech.ec.europa.eu/CITnet/jira/browse/SSF-120