## JIRA DATA
INSTRUCTIONS: Paste your JIRA export here (replace rows 3 onward, keep headers in row 2)
Issue Type | Issue key | Issue id | Summary | Status | Custom field (Epic Link) | Custom field (Story Points)
Story | SSF-215 | 4347715 | [BACK] Pending Hauls | Open | SSF-123 | 3.0
Story | SSF-140 | 4283057 | [MOB] Gear Management Screen | Ready | SSF-93 | 2.0

## DASHBOARD
REFINEMENT TRACKER - DASHBOARD
Last Updated |  | Current Sprint | 1
QUICK METRICS
Total Stories |  |  |  | Status
To Refine (Open) |  |  |  | Risk Level
Already Refined (Ready)
Completed So Far |  |  |  | Current Velocity
Remaining |  |  |  | Target Velocity | 6.5
Progress % |  |  |  | Projected Completion
SESSION SUMMARY (LAST 3)
| Session | Sprint | Date | Stories Refined | Cumulative | Status
WEEKLY REPORT (Auto-Generated)
Report Text

## SESSION LOG
SESSION LOG - Data Entry (Update After Each Session)
Session # | Sprint | Date | Day | Target Stories | Stories Refined (ENTER THIS) | Cumulative | Remaining | Velocity | Status | Notes/Blockers
1 | 1 | 2025-11-05 | Tuesday | 7 | 0 |  |  |  |  | Learning session
2 | 1 | 2025-11-07 | Thursday | 7 | 1 |  |  |  |  | Team alignment
3 | 1 | 2025-11-12 | Tuesday | 7
4 | 2 | 2025-11-19 | Tuesday | 7
5 | 2 | 2025-11-21 | Thursday | 7
6 | 2 | 2025-11-26 | Tuesday | 7
7 | 3 | 2025-12-03 | Tuesday | 7
8 | 3 | 2025-12-05 | Thursday | 7
9 | 3 | 2025-12-10 | Tuesday | 7
10 | 4 | 2025-12-17 | Tuesday | 7
11 | 4 | 2025-12-19 | Thursday | 7
12 | 4 | 2025-12-24 | Tuesday | 7
13 | 5 | 2026-01-07 | Tuesday | 7
14 | 5 | 2026-01-09 | Thursday | 7
15 | 5 | 2026-01-14 | Tuesday | 7
INSTRUCTIONS: Update ONLY column F after each session. Everything else auto-calculates!

## BURNDOWN CHART DATA
BURNDOWN CHART DATA
Session # | Sprint | Stories Remaining (Ideal) | Stories Remaining (Actual) | Variance | Status
0 | 1 |  |  | 0 | Start

## BURNUP CHART DATA
BURNUP CHART DATA
Session # | Sprint | Stories Refined (Target) | Stories Refined (Actual) | Total Scope | Gap
0 | 1 | 0 | 0 |  | 0

## EPIC PROGRESS
EPIC PROGRESS - Auto-calculated from JIRA DATA
Epic ID | Epic Name | Total | Open | Ready | Other | % Complete | Priority | Sprint
SSF-123 | Fishing Operations | [5 empty] | HIGH | 1-2
SSF-96 | Login & Session | [5 empty] | CRITICAL | 1
SSF-122 | Departure & Catches | [5 empty] | HIGH | 2-3
SSF-93 | Gear Management | [5 empty] | MEDIUM | 2-3
SSF-95 | Map & Location | [5 empty] | MEDIUM | 3-4
SSF-84 | Technical Setup | [5 empty] | HIGH | 1
SSF-165 | Backend Infrastructure | [5 empty] | MEDIUM | 4-5
SSF-166 | Internationalization | [5 empty] | LOW | 5
SSF-162 | Menu & Navigation | [5 empty] | MEDIUM | 3
SSF-94 | Home & Widgets | [5 empty] | MEDIUM | 2
SSF-86 | Tracking | [5 empty] | HIGH | 1
SSF-97 | CI/CD & Deployment | [5 empty] | MEDIUM | 4-5
SSF-132 | FMC Integration | [5 empty] | MEDIUM | 4

## SESSION CALENDAR
SESSION CALENDAR - All 13 Remaining Sessions
Session # | Sprint | Week | Date | Day | Time | Duration | Target | Prep Deadline | Status | Notes
3 | 1 | 2 | 2025-11-12 | Tue | 14:00 | 60 | 7 | 2025-11-10 | 🟡 This Week | Quick wins
4 | 2 | 1 | 2025-11-19 | Tue | 14:00 | 60 | 7 | 2025-11-17 | 🟢 Upcoming | Gear Backend
5 | 2 | 1 | 2025-11-21 | Thu | 14:00 | 60 | 7 | 2025-11-19 | 🟢 Upcoming | Gear Frontend
6 | 2 | 2 | 2025-11-26 | Tue | 14:00 | 60 | 7 | 2025-11-24 | 🟢 Upcoming | Map & Location
7 | 3 | 1 | 2025-12-03 | Tue | 14:00 | 60 | 7 | 2025-12-01 | 🟢 Upcoming | Departure Ops
8 | 3 | 1 | 2025-12-05 | Thu | 14:00 | 60 | 7 | 2025-12-03 | 🟢 Upcoming | Catches
9 | 3 | 2 | 2025-12-10 | Tue | 14:00 | 60 | 7 | 2025-12-08 | 🟢 Upcoming | Backend
10 | 4 | 1 | 2025-12-17 | Tue | 14:00 | 60 | 7 | 2025-12-15 | 🟢 Upcoming | Authentication
11 | 4 | 1 | 2025-12-19 | Thu | 14:00 | 60 | 7 | 2025-12-17 | 🟢 Upcoming | Infrastructure
12 | 4 | 2 | 2025-12-24 | Tue | 14:00 | 60 | 7 | 2025-12-22 | 🟢 Upcoming | Buffer
13 | 5 | 1 | 2026-01-07 | Tue | 14:00 | 60 | 7 | 2026-01-05 | 🟢 Upcoming | Final push
14 | 5 | 1 | 2026-01-09 | Thu | 14:00 | 60 | 7 | 2026-01-07 | 🟢 Upcoming | Final push
15 | 5 | 2 | 2026-01-14 | Tue | 14:00 | 60 | 7 | 2026-01-12 | 🟢 Upcoming | Completion